## Sheet3
Working week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
Starting date | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18
Sensing and Input | 2025-11-24: Read documentation Create/refine project plan Task assignment between members; 2025-12-01: Hardware improvement; 2025-12-08: Basic car control via dashboard; 2025-12-22: Camera handling (image reception, processing); 2026-04-20: Remaining bug fixes and patches Further refinement of sensors, inputs, perception, FSM,... Re-documentation of the code base A new dashboard (if possible); 2026-05-11: Prepare for a safe trip and good luck in BFMC2026 semi & finals!
Other sensors' handling (data retrieval from IMU, ToF)
Perception and scene understanding | 2025-12-08: Lane detection; 2025-12-29: Traffic light detection & classification; 2026-01-26: Vehicle detection; 2026-02-23: Pedestrian detection
[9 empty] | Traffic sign detection & classificaion |  |  |  |  | Combination between localization data and sensors' data
Behavior and motion plan working | 2025-12-29: Information communication and flow among internal components (should be splitted to 2 sth); 2026-02-16: Path finding and planning
[10 empty] | Communication and data retrieval from Traffic Communication Server |  |  |  |  | Definition & construction of a task-based FSM |  |  |  | Safe state-to-state switching flow
Vehicle control | 2025-12-01: Car Calibration; 2025-12-22: Lane keeping; 2026-01-19: Stop/ start at traffic light signal & stop lines; 2026-02-23: Stop when seeing vehicles; 2026-03-23: Stop when seeing pedestrian
[7 empty] | Speed control |  |  |  |  | Start/stop on traffic signs |  |  |  |  | Complex manuevers (intersection crossing, parking, overtaking
Final results and Demo | 2025-11-24: Team members know their main role and understand the basic working principle of the car's hardware and software; 2025-12-01: Make sure car works properly and is finely tuned Team has its own physical and virtual environment; 2025-12-22: Car can maintain itself in the designated lanes; 2026-01-19: Car can self-adhere to basic traffic rules; 2026-02-23: Car can ensure safety for all traffic participants; 2026-03-23: Car can handle its given tasks safely and efficiently; 2026-04-20: Make sure car still functions properly
|  | Team implemented virtual testing environment |  |  |  |  | Car can safely and smoothly run through multiple types of roads, especially ones with many sharp curves |  |  |  | Car can perceive environmental factors to plan safer and more efficient trips | [6 empty] | Car can perform most autonomous tasks smoothly |  |  |  | Improve car's navigability and efficiency
|  | Team creates own physical testing environment | [19 empty] | Make the code base more usable
Deadline | 2025-12-22: 2025-12-22; 2026-02-02: 2026-02-06; 2026-03-09: 2026-03-09; 2026-04-13: 2026-04-13
Checkpoint name | 2025-12-22: Project report 1; 2026-02-02: Project report 2; 2026-02-09: Lunar New Year break; 2026-03-09: Qualifications; 2026-04-13: Project report 3